Stanwood-Camano Early Learning

Our Promise:

Every student in the Stanwood-Camano School District is empowered to learn in an inclusive setting and

is prepared for the future of their choice.

| Area | 2021-2022 | 2022-2023 | 2023-2024 | 2024-2025 | 2025-2026 |
| --- | --- | --- | --- | --- | --- |
| Developmental Pre-School | Only service with no peer model program | Restructure to create 1 peer model section with 6 peer models and 5 students - special education <50% | Push-in with local pre-schools up to 11 slots; 2 peer model sections <50% | Push-in with local pre-schools and ECEAP up to 22 slots; 3 peer model sections at 50+%. | Push-in with local pre-schools and ECEAP up to 22 slots; 3 peer model sections at 50+%. |
| # of inclusive students | 0 | 5 | 21 | 37 | 37 |
| Transitional K | Planning phase for two classrooms; one on island, and one in town. Set board policy. Work with community resource center on recruitment. | Programs begin 2nd semester. Up to 50% special education students. |  | Additional classroom added. | In-town programs move to early learning center |
| # of inclusive students | 0 | 10 | 16 | 16 | 16 |
| Community Pre-Schools and ECEAP | Make contact and plan Summer introduction meeting | Three meetings with local pre-schools and ECEAP; Visits scheduled; Certificate given for participation and linkage with district. Research ECEAP slots. | Continue trimester meetings and on-site instruction in community pre-schools. Share WaKIDS data broken up by pre-school. Connect with ECEAP slots for following year | Ongoing meetings and shared professional development with pre-schools. Two ECEAP classrooms open | Ongoing meetings and shared professional development with pre-schools. Continued with two ECEAP classrooms |
| # of inclusive students | 0 | 0 | 9 | 18 | 18 |
| Facilities | SES - Three rooms | SES - Three rooms | Identify potential off-site location for early learning | Moving off-site; looking at bond for collective facility | Off-site learning center. Possible bond for early learning center |
| Staffing - Developmental Preschool | 2.5 FTE Certificated 37.2 hours Paraeducator | 3.0 FTE | 3.5 FTE | 4.0 FTE | 4.0 FTE |